## Read Me
Change KPI Dashboard – Enterprise GenAI & Cloud Transformation (Simulation)
Independent case study ¦ Freza Majithia ¦ 2026
IMPORTANT | All organizations, headcounts and weekly figures in this workbook are SIMULATED for illustration. Targets are proposed and would be calibrated against a real client baseline.
Purpose | Shows how a change team would track adoption of a generative AI productivity tool across four business departments (950 employees) during the first ~60 days of rollout, and how the data would drive decisions.
Sheets | Inputs – department set-up, proposed targets and weekly data (edit here). Dashboard – KPI summary, department view, insights and charts. Choose the reporting week in cell B4. Trends – calculation sheet that feeds the charts (no inputs).
Colour legend | Blue text = editable input or hardcoded sample value. Black text = formula. Green text = link to another sheet. Yellow fill = the cell(s) you choose or change most often.
KPI definitions | Training completion = cumulative employees who completed training ÷ employees in scope. Weekly active adoption = employees who used the tool that week ÷ employees in scope. Average sentiment = pulse-survey score (1–5), weighted by number of responses. Support tickets per 100 employees = tickets logged that week ÷ employees in scope × 100.
Status logic | On track = meets target. At risk = within the at-risk threshold of target (default 90%, see Inputs!G9). Off track = below that. Ramping up = the reporting week is earlier than the week the target applies from.
Data sources (real engagement) | Training completion – learning platform/LMS. Adoption – tool usage analytics (reported in aggregate only, never by individual). Sentiment – short weekly pulse survey. Tickets – service desk.
Design choices | Usage data is aggregated at department level to protect employee trust – the goal is to find where support is needed, not to monitor individuals.

## Dashboard
Change KPI Dashboard – Enterprise GenAI & Cloud Transformation (Simulation)
SIMULATED DATA for illustration. Targets are proposed and would be calibrated to a real client baseline.
Reporting week (1–9): | 9 | Change this cell to view any week. Week 9 ≈ day 60 of rollout.
KPI | Current | Target | Status | Definition
Training completion | 95.16% | 90% | On track | Cumulative employees trained ÷ employees in scope
Weekly active adoption | 71.16% | 75% | At risk | Employees using the tool that week ÷ employees in scope
Average sentiment (1–5) | 3.9611 | 4 | At risk | Pulse-survey score weighted by responses
Support tickets per 100 employees | 2.9474 | 5 | On track | Weekly tickets ÷ employees in scope × 100 (lower is better)
Department view – selected week
Department | Employees | Champions | Trained % | Weekly active % | Avg sentiment | Tickets /100 | Adoption status | Adoption target
Customer Service | 380 | 15 | 96.05% | 77.89% | 4.1 | 2.8947 | On track | 75%
Operations | 300 | 12 | 95% | 70% | 3.9 | 3 | At risk | 75%
Finance | 150 | 6 | 92% | 56% | 3.7 | 2.6667 | Off track | 75%
HR | 120 | 5 | 96.67% | 71.67% | 4 | 3.3333 | At risk | 75%
All departments | 950 | 38 | 95.16% | 71.16% | 3.9611 | 2.9474 | At risk | 75%
Insights (update automatically)
Highest adoption | Customer Service (78%)
Lowest adoption | Finance (56%)
Departments below adoption target | 3 of 4
Gap to target (all departments) | -3.8 percentage points vs target of 75%
Suggested focus | Prioritize champion support and role-specific use-case clinics in Finance; review what is working in Customer Service and share it.

## Inputs
Inputs – set-up, targets and weekly data
SAMPLE DATA – simulated for illustration. Blue cells are inputs; replace with real exports in a real engagement.
Department | Employees in scope | Champions | Note |  | KPI | Proposed target | Applies from week | Direction
Customer Service | 380 | 15 | ~1 champion per 25 employees (assumption) |  | Training completion | 90% | 4 | Higher is better
Operations | 300 | 12 | ~1 champion per 25 employees (assumption) |  | Weekly active adoption | 75% | 9 | Higher is better
Finance | 150 | 6 | ~1 champion per 25 employees (assumption) |  | Average sentiment (1–5) | 4 | 9 | Higher is better
HR | 120 | 5 | ~1 champion per 25 employees (assumption) |  | Support tickets per 100 employees | 5 | 9 | Lower is better
Total in scope | 950 | 38 | Remaining ~250 of 1,200 employees (IT & Cloud Engineering, leadership) are not in the Wave 1 tool rollout. |  | At-risk threshold (share of target) | 90%
Targets are illustrative proposals; week 9 ≈ day 60 of rollout. Set them against a real baseline.
Week | Department | Employees trained (cumulative) | Weekly active users | Pulse survey responses | Avg sentiment (1–5) | Support tickets (that week) |  | Legend
1 | Customer Service | 76 | 30 | 152 | 3 | 15 |  | Blue = input / sample value
1 | Operations | 45 | 15 | 120 | 2.9 | 12 |  | Black = formula
1 | Finance | 27 | 6 | 60 | 2.7 | 6 |  | Example row = Week 1, Customer Service
1 | HR | 30 | 12 | 48 | 3.1 | 5
2 | Customer Service | 190 | 76 | 152 | 3.2 | 27
2 | Operations | 126 | 42 | 120 | 3 | 21
2 | Finance | 68 | 15 | 60 | 2.8 | 10
2 | HR | 72 | 29 | 48 | 3.3 | 8
3 | Customer Service | 296 | 137 | 152 | 3.4 | 34
3 | Operations | 210 | 81 | 120 | 3.2 | 27
3 | Finance | 99 | 27 | 60 | 2.9 | 14
3 | HR | 102 | 48 | 48 | 3.5 | 11
4 | Customer Service | 353 | 190 | 152 | 3.6 | 30
4 | Operations | 270 | 120 | 120 | 3.4 | 24
4 | Finance | 123 | 42 | 60 | 3.1 | 12
4 | HR | 114 | 65 | 48 | 3.7 | 10
5 | Customer Service | 361 | 228 | 152 | 3.8 | 23
5 | Operations | 279 | 150 | 120 | 3.6 | 18
5 | Finance | 132 | 54 | 60 | 3.3 | 9
5 | HR | 115 | 76 | 48 | 3.8 | 7
6 | Customer Service | 361 | 258 | 152 | 3.9 | 19
6 | Operations | 282 | 174 | 120 | 3.7 | 15
6 | Finance | 135 | 64 | 60 | 3.4 | 8
6 | HR | 115 | 82 | 48 | 3.9 | 6
7 | Customer Service | 365 | 277 | 152 | 4 | 15
7 | Operations | 282 | 192 | 120 | 3.8 | 12
7 | Finance | 136 | 74 | 60 | 3.5 | 6
7 | HR | 116 | 84 | 48 | 3.9 | 5
8 | Customer Service | 365 | 289 | 152 | 4.1 | 13
8 | Operations | 285 | 204 | 120 | 3.9 | 10
8 | Finance | 138 | 80 | 60 | 3.6 | 5
8 | HR | 116 | 85 | 48 | 4 | 4
9 | Customer Service | 365 | 296 | 152 | 4.1 | 11
9 | Operations | 285 | 210 | 120 | 3.9 | 9
9 | Finance | 138 | 84 | 60 | 3.7 | 4
9 | HR | 116 | 86 | 48 | 4 | 4

## Trends
Trends – calculation sheet for dashboard charts (no inputs)
Week | Customer Service | Operations | Finance | HR | Overall adoption | Adoption target | Overall training completion | Overall sentiment | Sentiment target | Tickets per 100 employees | Tickets target
1 | 7.895% | 5% | 4% | 10% | 6.632% | 75% | 18.74% | 2.9337 | 4 | 4 | 5
2 | 20% | 14% | 10% | 24.17% | 17.05% | 75% | 48% | 3.0863 | 4 | 6.9474 | 5
3 | 36.05% | 27% | 18% | 40% | 30.84% | 75% | 74.42% | 3.2705 | 4 | 9.0526 | 5
4 | 50% | 40% | 28% | 54.17% | 43.89% | 75% | 90.53% | 3.4705 | 4 | 8 | 5
5 | 60% | 50% | 36% | 63.33% | 53.47% | 75% | 93.37% | 3.6579 | 4 | 6 | 5
6 | 67.89% | 58% | 42.67% | 68.33% | 60.84% | 75% | 94% | 3.7579 | 4 | 5.0526 | 5
7 | 72.89% | 64% | 49.33% | 70% | 66% | 75% | 94.63% | 3.8453 | 4 | 4 | 5
8 | 76.05% | 68% | 53.33% | 70.83% | 69.26% | 75% | 95.16% | 3.9453 | 4 | 3.3684 | 5
9 | 77.89% | 70% | 56% | 71.67% | 71.16% | 75% | 95.16% | 3.9611 | 4 | 2.9474 | 5